## Guidance
Cells | Guidance
Cell C3-C5 | Please completed with your Health and Wellbeing board, contact name and e-mail address
C13-C20 - Discharges from hospital, by service | Please provide best available data on the number of discharges from acute settings into the settings listed, for the 14 day period specified. If data does not fit into the categories listed, please use the other pathway lines to capture these discharges. Please input only a number and, if needed, provide a short description in the notes column of any discrepancies your data may have
D26-D30 - Packages of care booked or used, by type of service, for all local authority funded social care | Please provide best available data on the overall number hours of care, packages of care or care home beds funded by the local authority during the reporting period that are currently in use or available (have been booked), not limited to those provided following discharge from hospital, by service type. Please note, this should exclude any spend from the ASC Discharge fund. Please input only a number and, if needed, provide a short description in the notes column of any discrepancies your data may have
E26-E30 - Packages of care booked or used, by type of service, funded by the £500m Adult Social Care Discharge Fund (ASC DF) | Please provide best available data on the overall number hours of care, packages of care or care home beds funded by the Adult Social Care Discharge fund (ASC DF) during the reporting period that are currently in use or available, not limited to those provided following discharge from hospital, by service type. If needed, please provide a short description in the notes column of any discrepancies your data may have
C35-D44 - Spend during this reporting period, by service type | Please provide the value of spend from each of the LA and ICB allocations of the ASC DF, formally committed or contracted to date since the discharge fund commenced, by service type. Payments need not to have been made in order for it to be recorded here. For each spend area please provide a description in the notes column outlining what the fund is purchasing.
F35-F44- Estimate of residual shortfall in available provision | Please estimate the extent to which demand for each service is met. You should only consider demand for this service to support discharge, rather than adult social care demand overall.
C52-C56 - Narrative of progress | Please use this space to describe progress made in the last 2 weeks to use the additional funding to improve discharge outcomes. Where possible, please also give an indication of realised or expected impact on reducing delays.
C61-C62 - Information to support evaluation | To support the evaluation of the fund, please use this section briefly to describe any barriers or challenges to spending the adult social care discharge funding and the level of confidence you have that the funding will support reductions in discharge delays.
Notes (D13-D20), (G26-F30) | If needed, please provide a short description of any discrepancies your data may have
Notes (G35:G44) | For each spend areas, please provide a short description of what the fund is purchasing

## Activity Report
Adult Social Care Discharge Fund 2022-23 Activity Reporting Template
Heath and Wellbeing Board | Cornwall & Scilly
Contact Name | s40 redaction
Email | s40 redaction
As a condition of this funding for health and social care to improve hospital discharge, local Health and Wellbeing Board areas should report as required on the additional activity and services that have been delivered using the funding.
When reporting the numbers of packages funded from the Adult Social Care Discharge Fund (ASC DF), please use this template to report on new packages for the reporting period and spend since the ASC DF commenced.
Please input figures manually into this template, and do not copy and paste the template into another document.
If unclear, please use guidance on the first tab to obtain more information on the requirements for each cell
1. Number of discharges from hospital by service (14 day period from 19/01/23 to 01/02/23)
Discharge Setting | Number of discharges | Notes
Home or domiciliary care | 235 | Further to previous reporting and commentary therein Cornwal is including dicharges from Community Hospital Settings owing to the importance to overall flow picture of these settings Figure is ALL P1 discharges - Acute only = 137
Reablement in a person's own home
Residential care
Nursing care | 77 | Figure is ALL P3 discharges - Acute only = 39
Intermediate care | 175 | Figure is ALL P2 discharges - Acute only = 173
Other pathway one support
Other pathway two support
Other pathway three support
Total | 487
2. Packages of care booked or in use for all local authority funded social care (14 day period from 19/01/23 to 01/02/23)
Discharge Setting | Unit | Local authority funded social care | Funded via ASC Discharge Fund | Total | Notes
Home or domiciliary care | Hours | 58297 | 225 | 58522 | In scope packages apportioned and not therefore reporting full period effect of 259 hrs per week
Reablement in a person's own home | Hours | 2460 | 0 | 2460 | Please be advised that ASC commisioned reablement provider also provides Provider of Last Resort support to area - experiencing significant demand on workforce following x2 homecare provider failures and attrition of TUPE'd workforce
Residential care | Number of Beds | 1570 | 15 | 1585
Nursing care | Number of Beds | 579 | 8 | 587
Intermediate care | Number of Beds | 0 | 0 | 0 | Please note that all bedded intermediate care is commissioned locally by ICB
3. Adult Social Care Discharge Fund (total spending to date)
Service type | Spend from ICB allocation to date | Spend from LA allocation to date | Total Spend to date(£) | With this spending, to what extent do you currently have the capacity to meet need to discharge people into adult social care? | Notes
Home care or domiciliary care (long term) | 0 | 42718.28 | 42718.28 |  | Spend from LA Allocation represents packages placed in market since engagment activity for ASC Scheme 6 commenced
Home care or domiciliary care (short term - up to 6 weeks) | 0 | 0 | 0
Bed based intermediate care services | 50000 | 0 | 50000
Reablement in a person's own home | 44768 | 0 | 44768
Care home placements (residential - short term - up to 6 weeks) | 92409.24 | 0 | 92409.24
Care home placements (residential - long term) | 0 | 232481.3 | 232481.3
Residential placements (complex/nursing) | 0 | 181583.77 | 181583.77 |  | Please note further ICB discharges under ICB 3A (supported ICB 3B) to be reconciled for spend at time of writing
Workforce recruitment and retention | 0 | 21000 | 21000
Assistive technology and equipment | 89844.3 | 38504.7 | 128349
Spend on any other areas (e.g. admin, contingency etc. Outline any spend here in notes section) | 0 | 0 | 0
Total | 277021.54 | 516288.05 | 793309.59
4. Additional Narrative
Narrative section 1 - Description of progress
Please use the space below each theme to describe progress made in this period to use the additional funding to improve discharge outcomes. Where possible, please also give an indication of realised or expected impact on reducing delays. Where you have identified a shortfall in capacity, indicate the main causal factors. This might include:
Theme | Answer
i) Progress in securing additional workforce, or increasing hours worked by the existing workforce | The recruitment campaign funded by ASC Scheme 10 is proving effective. A 'Hiring' event on 28th Jan, widely pre-publiced locally with radio and bus-stop adverts, where attendees were to an extent pre-reviewed and therefore in principle appointable, and themsleves invested in the process, led to 7 offers of employment accepted on the day and a further 25 offers of employment being considered. Following the apparent success of this event work is ongoing to replicate it in other towns in Cornwall during the period for which funding is available. In addition this scheme is projected to spend a further £82,000. The offer of optimised homecare bundles funded via ASC Scheme 6 appears to have been succesful, when procurement closed firm offers had been received from 17 providers. Evaluation and award is in progress at the time of writing however and projections as to mobilisation and spend from the fund will feature in future reporting. The funding assigned to create additional assessing capacity is being utilised initially to fund social work overtime. Some 43 individuals have volunteered to work additional hours undertaking assessments since the offer was made during this reporting period. The ICB have scheduled engagement meetings with care providers to discuss the co-design of workforce initiatives; this will have a longer term impact on recruitment and retention. The increase in the rate cap has enabled additional placements to be made available to facilitate discharge; this has directly impacted a number of discharges during this period.
ii) Progress in commissioning additional domiciliary care and intermediate care capacity | ASC Scheme 6, the offer of bundled homecare provision had a closing date of 31st January. Initial indications are that this has led to potential for market growth with a number of new entrants locally submitting credible bid which are anticipated to proceed. The market engagement for this activity (during the previous reporting period) additionally had a tangible impact on the existing market leading to an increasing number of offers and reductions in all unmet demand including individuals whose delay in being found care exerts a negative influence on flow. ICB Discussions with care provider groups has enabled additional capacity to be made available to support additional discharges; selected care homes have agreed additional beds. New short-term enablement capacity (12 beds) has been secured and will be accepting discharges from 13/2. Environmental work to support preparedness has been undertaken with invoices moving to workflow.
iii) Other activity funded through this additional funding | Progress has been made to bring capacity online faster than planned for ICB scheme 3a. 5 beds are now live and 5 additional beds will come online weekly until the 25 are active. There is medical cover being provided to support these individuals and that will also be reflected in future submissions. We have doubled the commitment from our provider to deliver an additional 10 places (discharges) per week. This enhanced capacity in the community is being repeated through commissioning a service across the remaining 2 ICA places with an expectation this will come online during February following due governance. We have also worked with a provider to deliver additional discharges into a temporary bedded facility. This is a fast-tracked scheme that will start to accept placements from the 13th Feb and steadily build to deliver 12 beds with an anticipated placement being less than 2 weeks. There has been an expansion of the care homes support team and this additional resource will develop the offer of facilitating discharge over the next few weeks (subject to personnel being transferred into the service).
iv) New/innovative initiatives | The deployment, under ASC Scheme 10, of an Indeed 'hiring event' has proven successful and will likely be repeated with a single day yielding 32 firm offers of employment to pre-reviewed candidates who attended in person for direct conversation with Home Care provider personnel including those mandated to offer employment to suitable candidates
v) Any other themes
Narrative section 2 - Information to support evaluation
Please use this section to briefly describe: | Answer
i) Any barriers/challenges you have faced in spending the ASC DF | ICB Providers had already been tasked with delivering additional capacity for winter. This fund has restarted the commissioning process for capacity in excess of this and will only impact in the second half of the period. Fewer providers bid for reablement opportunities, so we will have slippage on this element that we are mitigating through additional initiatives.
ii) Level of confidence in your ability to spend the funding to impact on discharge delays. | As with any system there is a lead-time to providing any additional capacity for specific pathways, but providers are undertaking recruitment and training to assist with making this happen.
Once completed, this activity return should be sent to england.bettercarefundteam@nhs.net by 3rd February 2023.

## dropdown (hidden)
ASC Discharge Fund Spending to date percentages | HWB
100% | Barking and Dagenham
75-99% | Barnet
50-74% | Barnsley
25-49% | Bath and North East Somerset
<25% | Bedford
0% | Bexley
Birmingham
Blackburn with Darwen
Blackpool
Bolton
Bournemouth, Christchurch and Poole
Bracknell Forest
Bradford
Brent
Brighton and Hove
Bristol, City of
Bromley
Buckinghamshire
Bury
Calderdale
Cambridgeshire
Camden
Central Bedfordshire
Cheshire East
Cheshire West and Chester
City of London
Cornwall & Scilly
County Durham
Coventry
Croydon
Cumbria
Darlington
Derby
Derbyshire
Devon
Doncaster
Dorset
Dudley
Ealing
East Riding of Yorkshire
East Sussex
Enfield
Essex
Gateshead
Gloucestershire
Greenwich
Hackney
Halton
Hammersmith and Fulham
Hampshire
Haringey
Harrow
Hartlepool
Havering
Herefordshire, County of
Hertfordshire
Hillingdon
Hounslow
Isle of Wight
Islington
Kensington and Chelsea
Kent
Kingston upon Hull, City of
Kingston upon Thames
Kirklees
Knowsley
Lambeth
Lancashire
Leeds
Leicester
Leicestershire
Lewisham
Lincolnshire
Liverpool
Luton
Manchester
Medway
Merton
Middlesbrough
Milton Keynes
Newcastle upon Tyne
Newham
Norfolk
North East Lincolnshire
North Lincolnshire
North Northamptonshire
North Somerset
North Tyneside
North Yorkshire
Northumberland
Nottingham
Nottinghamshire
Oldham
Oxfordshire
Peterborough
Plymouth
Portsmouth
Reading
Redbridge
Redcar and Cleveland
Richmond upon Thames
Rochdale
Rotherham
Rutland
Salford
Sandwell
Sefton
Sheffield
Shropshire
Slough
Solihull
Somerset
South Gloucestershire
South Tyneside
Southampton
Southend-on-Sea
Southwark
St. Helens
Staffordshire
Stockport
Stockton-on-Tees
Stoke-on-Trent
Suffolk
Sunderland
Surrey
Sutton
Swindon
Tameside
Telford and Wrekin
Thurrock
Torbay
Tower Hamlets
Trafford
Wakefield
Walsall
Waltham Forest
Wandsworth
Warrington
Warwickshire
West Berkshire
West Northamptonshire
West Sussex
Westminster
Wigan
Wiltshire
Windsor and Maidenhead
Wirral
Wokingham
Wolverhampton
Worcestershire
York